## Notes
RISK MANAGEMENT PLAN - NOTES
Terminology Used.
Gross Risk - measure of risk posed if no action taken. Impact multiplied by likelihood.
Mitigation - action to be taken to minimise impact if risk did occur.
Avoidance - action to be taken to prevent risk occurring.
Mitigation % - reduction in impact anticipated. For example, 50% would reduce impact by half.
Avoidance % - reduction in likelihood anticipated. For example, 75% would reduce likelihood by three quarters.
Net risk - overall risk if mitigation/avoidance strategies implemented.
Total Risk - the first Total Gross Risk is a measure of overall risk if no action taken and the second (Net Risk) the reduced level of risk if it is.
Upside Risk - the risk of an unexpected good outcome happening - score as a negative, because it reduces risk.
Risk Appetite - how much risk an organisation is willing to accept.
Resources cannot cover every aspect for every charity, nor all circumstances,
nor does this constitute professional advice; https://www.charityexcellence.co.uk Alumna © 2017

## Risk Management Plan
ONB ASA RISK REGISTER
Creation date: November 2023
Next review date: August 2024
Risk | Date logged | Risk owner | Impact | Likelihood | Gross Risk | Mitigation - what we need to do to minimise impact | Completion date for orange or red gross risk | Jun 24 update on orange or red gross risk
Legal structures, governance and liabilities
ONB as an unincorporated association with liability on the officers. | 2023-11-01 | Chair | 5 | 2 | 10 | Move to ONB becoming a Charitable Incorporated Organisation Association. | 2025-07-01 | This has been moved back a year to Jul 25. Now that most of the key posts are filled and the SE governance code almost completed, we can move onto incorporation.
Swim England governance requirements not submitted by 31/12/2023. | 2023-11-01 | Treasurer | 2 | 5 | 10 | Revised constiution needs to be adopted at a Special General meeting in Jan 24. Governance requirements will then be met and submitted. | 2024-01-01 | Hope to achieve by end of July 24 once Welfare Officer statement of compliance is uploaded.
Swim England governance requirements not updated annually. | 2023-11-01 | Treasurer | 1 | 3 | 3 | Ongoing update of the portal with relevant documents when they are changed/amended.
Risk register is not monitored and reviewed by the executive board. | 2023-11-01 | Treasurer | 4 | 1 | 4 | Risk register is a standing item at each executive meeting.
Decisions of the executive board are not clear to all members. | 2023-11-01 | Secretary | 4 | 1 | 4 | Clear decisions and actions in minutes published on website
Committee
Unable to recruit key board members. | 2023-11-01 | Chair | 5 | 2 | 10 | Succession plan statement in place. Succession planning is a standing item on each executive meeting agenda. | 2024-07-01 | This has moved back to orange given new appointments of key post holders at AGM Jul 24. Still needs to be monitored to ensure sustainability.
Executive board is not effective. | 2023-11-01 | Chair | 5 | 1 | 5 | Succession plan statement in place. This states the skills and capabilities required for key board members.
Policies and procedures
Safeguarding policy is not adopted and communicated with clubs. | 2023-11-01 | Welfare Officer | 5 | 1 | 5 | Safeguarding policy adopted (WavePower) and shared with clubs.
Finance and sustainability |  |  |  |  | 0
Poor accounting software leads to loss of financial data. | 2023-11-01 | Treasurer | 2 | 3 | 6 | Move to up to date and cloud based accounting software in next financial year. Paper copies kept as back up at present. |  | We are now using Excel which is cloud based.
Insecurity around Metro Bank's viability. | 2023-11-01 | Treasurer | 5 | 3 | 15 | Keep money within Barclays' accounts at present. Monitor the situation with Metro Bank. | 2025-04-01 | Money is with Barclays as Metro still have issues. Needs review once CIOA status is in place as we will have to talk to the banks about this and the impact on our accounts.
Poor financial forecasting affecting viability. | 2023-11-01 | Treasurer | 5 | 1 | 5 | Budget and cashflow reports at each executive meeting. Maintain £16,000 in reserve.
The potenial for fraudulent activity. | 2023-11-01 | Treasurer | 5 | 1 | 5 | Dual signatories required on all bank accounts. Cash at the Counties is kept to a minimum, is checked by two people before handing to the Treasurer who banks the money within 7 working days.
Legal and reporting requirements
Health and safety issues not reported to the executive meeting. | 2023-11-01 | Chair | 5 | 2 | 10 | Any health and safety concerns at County organised events/activities are reported by the event/activity organiser to the Chair who in turn reports to the next executive meeting. | 2024-07-01 | On track.
Risk assessments for ONB organised events do not use the Swim England template and guidance. | 2023-11-01 | Chair | 4 | 3 | 12 | All ONB events to use Swim England risk assessment template and refer to Swim England guidance so that Swim England insurance could not be considered void if there is a future incident. | 2024-07-01 | On track.
Human resources
Contracts for coaches/team managers on development camps not in place. | 2023-11-01 | Chair | 3 | 3 | 9 | Contracts written so roles, responsibilities and expectations are clear. The legal status of the allowances for Head Coach, Team Manager and Lane/Skills Coach status to be reviewed to ensure that they meet HMRC requirements. | 2025-04-01 | This is to be pushed back to Apr 25.
Insurance
Adequate Professional Indemnity and Public Liability Insurance Cover in place. | 2023-11-01 | Chair | 5 | 2 | 10 | Swim England insurance in place. Change of status to Charitable Incorporated Organisation Association will move most liabilities away from the Key Officers. | 2025-07-01 | Moved to Jul 25 to link with CIOA status.
Major event or no pool time means an event does not not ahead. | 2023-11-01 | Chair | 5 | 1 | 5 | Business interruption insurance cover in place. Pool time booked significantly in advance to ensure availability.
Safeguarding
ONB complies with OMS requirements for DBS and safeguarding CPD. | 2023-11-01 | Secretary | 5 | 1 | 5 | ONB OMS tracker spreadsheet in place to ensure year DBS and relevant safeguarding CPD in place and current.
GDPR
ONB meets legal requirements for registration with Information Commissioners Office (ICO). | 2023-11-01 | Treasuer | 5 | 1 | 5 | Annual check that ONB continues to be ICO registration exempt.
Possible data breaches of swimmers' personal data. | 2023-11-01 | County Swim Secretary | 2 | 2 | 4 | Clear destruction policy in place at County Championships. Swimmer data only held on County owned laptops.
Inclusion and equality
Events/activities/executive board are not accessible to participants and volunteers. | 2023-11-01 | Chair | 5 | 2 | 10 | Diversity and inclusion action plan in place. | 2024-07-01 | See DIAP report
Membership and participant numbers
Members do not want to transfer to new CIOA. | 2023-11-01 | Chair | 1 | 4 | 4 | Swim England advice sought and member clubs have to be part of any agreed structure.
Members are not engaging with ONB. | 2023-11-01 | Chair | 4 | 3 | 12 | Club voice incorporated into the new CIOA. | 2025-07-01 | Moved back to Jul 25 to link with CIOA status.
Volunteer numbers
Lack of officials for the County Championships. | 2023-11-01 | Officials Coordinator | 4 | 2 | 8 | ONB to continue to support J1 trainees and their clubs through clubs being able to recoup the £10 cost for J1 training voucher from ONB onec the J1 has been successfully completed.
Swim England ratios for Development Camps and InterCounties are met. | 2023-11-01 | County Coordinator | 1 | 4 | 4 | Head Coach and Lead Team Manager work with County Coordinator to appoint a Boys Team Manager.
Facilities and equipment
Electrical safety of ONB equipment. | 2023-11-01 | County Swim Secretary | 2 | 4 | 8 | PAT testing of ONB electrical equipment takes place as per HSE recommendations/requirements.
| Likelihood |  |  | Impact |  | Overall rating
| Very unlikely | 1 |  | Very low | 1 | Low | 1 to 8
| Unlikely | 2 |  | Low | 2 | Medium | 9 to 17
| Neither likely or unlikely | 3 |  | Medium | 3 | High | 18 to 25
| Likely | 4 |  | High | 4
| Very likely | 5 |  | Very high | 5